## Overall Progress
Thematic Area | Legacy Tool Count | Ported Tool Count | Remaining To Port | Percent Complete | Primary Tier | Notes
Agriculture | 6 | 6 | 0 | 100 | wbtools_pro | All Pro-tier precision agriculture tools; full callback support
Data Tools | 27 | 27 | 0 | 100 | wbtools_oss | Format conversion and vector cleansing; geometry validation
Geomorphometry | 100 | 100+ | 0 | 100 | wbtools_oss/pro | Parity + modernized implementations; multi-scale analysis
GIS (Overlay/Analysis) | 102 | 105 | 0 | 102.9 | wbtools_oss/pro | Raster overlay + aggregation/interpolation + workflow wrappers; 3 new enhancements
Hydrology | 60 | 60 | 0 | 100 | wbtools_oss | Depression removal + flow algorithms + diagnostics + watersheds
Remote Sensing | 82 | 82+ | 0 | 100 | wbtools_oss/pro | Image filters + classification + ML; enhanced implementations
LiDAR Processing | 63 | 64 | 0 | 101.6 | wbtools_oss/pro | Phases 1-3 done; CRS propagation; batch-mode support; 1 dormant legacy exception + 1 workflow wrapper
Stream Network Analysis | 26 | 29 | 0 | 111.5 | wbtools_oss/pro | Stream ordering + magnitude + link analysis + vector topology repair + workflow wrappers
Math & Statistics | 99 | 98 | 0 | 99 | wbtools_oss | All legacy except 1 intentional exception (hdbscan_clustering)

## Agriculture
New_Tool_Name | Legacy_Tool_Name | Port_Tier | Port_Status | Is_New_NonLegacy | Notes | Python_Wrapper_Status
recreate_pass_lines | recreate_pass_lines | wbtools_pro | done | No | Tier: wbtools_pro ¦ Pass-line reconstruction from yield data
yield_filter | yield_filter | wbtools_pro | done | No | Tier: wbtools_pro ¦ Statistical outlier filtering in yield maps
yield_map | yield_map | wbtools_pro | done | No | Tier: wbtools_pro ¦ Yield polygon generation from pass lines
yield_normalization | yield_normalization | wbtools_pro | done | No | Tier: wbtools_pro ¦ Yield standardization and scaling
remove_field_edge_points | remove_field_edge_points | wbtools_pro | done | No | Tier: wbtools_pro ¦ Edge-effect removal from yield data
reconcile_multiple_headers | reconcile_multiple_headers | wbtools_pro | done | No | Tier: wbtools_pro ¦ Multi-header yield aggregation

## Data Tools
New_Tool_Name | Legacy_Tool_Name | Port_Tier | Port_Status | Is_New_NonLegacy | Notes | Python_Wrapper_Status
add_point_coordinates_to_table | add_point_coordinates_to_table | wbtools_oss | done | No | Tier: wbtools_oss ¦ Append XCOORD, YCOORD fields from point geometry
clean_vector | clean_vector | wbtools_oss | done | No | Tier: wbtools_oss ¦ Remove null and invalid geometries
convert_nodata_to_zero | convert_nodata_to_zero | wbtools_oss | done | No | Tier: wbtools_oss ¦ Replace nodata with 0
csv_points_to_vector | csv_points_to_vector | wbtools_oss | done | No | Tier: wbtools_oss ¦ Import point features from CSV
export_table_to_csv | export_table_to_csv | wbtools_oss | done | No | Tier: wbtools_oss ¦ Export attribute table to CSV
fix_dangling_arcs | fix_dangling_arcs | wbtools_oss | done | No | Tier: wbtools_oss ¦ Snap undershot/overshot line endpoints
join_tables | join_tables | wbtools_oss | done | No | Tier: wbtools_oss ¦ Join attribute tables by field
lines_to_polygons | lines_to_polygons | wbtools_oss | done | No | Tier: wbtools_oss ¦ Close line features into polygons
merge_table_with_csv | merge_table_with_csv | wbtools_oss | done | No | Tier: wbtools_oss ¦ Merge CSV data into attribute table
merge_vectors | merge_vectors | wbtools_oss | done | No | Tier: wbtools_oss ¦ Combine multiple vector layers
modify_nodata_value | modify_nodata_value | wbtools_oss | done | No | Tier: wbtools_oss ¦ Change nodata value in raster
multipart_to_singlepart | multipart_to_singlepart | wbtools_oss | done | No | Tier: wbtools_oss ¦ Explode multipart geometries
new_raster_from_base_raster | new_raster_from_base_raster | wbtools_oss | done | No | Tier: wbtools_oss ¦ Create blank raster from template
new_raster_from_base_vector | new_raster_from_base_vector | wbtools_oss | done | No | Tier: wbtools_oss ¦ Create blank raster from vector extent
polygons_to_lines | polygons_to_lines | wbtools_oss | done | No | Tier: wbtools_oss ¦ Convert polygon boundaries to lines
print_geotiff_tags | print_geotiff_tags | wbtools_oss | done | No | Tier: wbtools_oss ¦ Display GeoTIFF metadata tags
raster_to_vector_lines | raster_to_vector_lines | wbtools_oss | done | No | Tier: wbtools_oss ¦ Vectorize raster line features
raster_to_vector_polygons | raster_to_vector_polygons | wbtools_oss | done | No | Tier: wbtools_oss ¦ Vectorize raster polygon patches
raster_to_vector_points | raster_to_vector_points | wbtools_oss | done | No | Tier: wbtools_oss ¦ Sample raster as point features
reinitialize_attribute_table | reinitialize_attribute_table | wbtools_oss | done | No | Tier: wbtools_oss ¦ Reset attribute table structure
remove_polygon_holes | remove_polygon_holes | wbtools_oss | done | No | Tier: wbtools_oss ¦ Remove holes from polygon features
remove_raster_polygon_holes | remove_raster_polygon_holes | wbtools_oss | done | No | Tier: wbtools_oss ¦ Remove holes from raster patches
set_nodata_value | set_nodata_value | wbtools_oss | done | No | Tier: wbtools_oss ¦ Define nodata value in raster
singlepart_to_multipart | singlepart_to_multipart | wbtools_oss | done | No | Tier: wbtools_oss ¦ Merge single geometries into multi-part
vector_lines_to_raster | vector_lines_to_raster | wbtools_oss | done | No | Tier: wbtools_oss ¦ Rasterize line features
vector_polygons_to_raster | vector_polygons_to_raster | wbtools_oss | done | No | Tier: wbtools_oss ¦ Rasterize polygon features
vector_points_to_raster | vector_points_to_raster | wbtools_oss | done | No | Tier: wbtools_oss ¦ Rasterize point features

## Geomorphometry
New_Tool_Name | Legacy_Tool_Name | Port_Tier | Port_Status | Is_New_NonLegacy | Notes | Python_Wrapper_Status
aspect | aspect | wbtools_oss | done | No | Tier: wbtools_oss ¦ Slope aspect in degrees clockwise from north
slope | slope | wbtools_oss | done | No | Tier: wbtools_oss ¦ Slope gradient (degrees/radians/percent)
elevation_percentile | elevation_percentile | wbtools_oss | done | No | Tier: wbtools_oss ¦ Elevation ranking within terrain context
curvedness | curvedness | wbtools_pro | done | No | Tier: wbtools_pro ¦ Combined curvature magnitude
mean_curvature | mean_curvature | wbtools_oss | done | No | Tier: wbtools_oss ¦ Average principal curvature
profile_curvature | profile_curvature | wbtools_oss | done | No | Tier: wbtools_oss ¦ Slope curvature in flow direction
plan_curvature | plan_curvature | wbtools_oss | done | No | Tier: wbtools_oss ¦ Slope curvature perpendicular to flow
tangential_curvature | tangential_curvature | wbtools_oss | done | No | Tier: wbtools_oss ¦ Contour curvature; alternative: plan curvature
total_curvature | total_curvature | wbtools_oss | done | No | Tier: wbtools_oss ¦ Sum of absolute principal curvatures
casorati_curvature | casorati_curvature | wbtools_oss | done | No | Tier: wbtools_oss ¦ Casorati curvature (Gaussian/product curvature)
gaussian_curvature | gaussian_curvature | wbtools_oss | done | No | Tier: wbtools_oss ¦ Product of principal curvatures
horizontal_excess_curvature | horizontal_excess_curvature | wbtools_pro | done | No | Tier: wbtools_pro ¦ Plan curvature excess
vertical_excess_curvature | vertical_excess_curvature | wbtools_pro | done | No | Tier: wbtools_pro ¦ Profile curvature excess
maximal_curvature | maximal_curvature | wbtools_oss | done | No | Tier: wbtools_oss ¦ Maximum principal curvature
minimal_curvature | minimal_curvature | wbtools_oss | done | No | Tier: wbtools_oss ¦ Minimum principal curvature
difference_curvature | difference_curvature | wbtools_pro | done | No | Tier: wbtools_pro ¦ Curvature difference metric
ring_curvature | ring_curvature | wbtools_pro | done | No | Tier: wbtools_pro ¦ Circular terrain curvature
accumulation_curvature | accumulation_curvature | wbtools_pro | done | No | Tier: wbtools_pro ¦ Flow-weighted curvature
multiscale_curvatures |  | wbtools_pro | done | Yes | Tier: wbtools_pro ¦ Multi-scale curvature analysis; NEW_ENHANCEMENT
hillshade | hillshade | wbtools_oss | done | No | Tier: wbtools_oss ¦ Shaded relief visualization
sky_view_factor | sky_view_factor | wbtools_pro | done | No | Tier: wbtools_pro ¦ Sky visibility index (0-1)
openness | openness | wbtools_pro | done | No | Tier: wbtools_pro ¦ Positive and negative openness metrics
visibility_index | visibility_index | wbtools_oss | done | No | Tier: wbtools_oss ¦ Terrain visibility from point/raster
viewshed | viewshed | wbtools_oss | done | No | Tier: wbtools_oss ¦ Grid-based viewshed from DEM
horizon_angle | horizon_angle | wbtools_oss | done | No | Tier: wbtools_oss ¦ Maximum horizon angle from point
horizon_area | horizon_area | wbtools_pro | done | No | Tier: wbtools_pro ¦ Terrain area visible to horizon
average_horizon_distance | average_horizon_distance | wbtools_pro | done | No | Tier: wbtools_pro ¦ Mean visible distance to horizon
exposure_towards_wind_flux | exposure_towards_wind_flux | wbtools_oss | done | No | Tier: wbtools_oss ¦ Wind exposure metric
ruggedness_index | ruggedness_index | wbtools_oss | done | No | Tier: wbtools_oss ¦ Terrain roughness index
surface_area_ratio | surface_area_ratio | wbtools_oss | done | No | Tier: wbtools_oss ¦ Actual vs. projected surface area
slope_vs_aspect_plot | slope_vs_aspect_plot | wbtools_pro | done | No | Tier: wbtools_pro ¦ Diagnostic visualization
slope_vs_elev_plot | slope_vs_elev_plot | wbtools_oss | done | No | Tier: wbtools_oss ¦ Diagnostic visualization
standard_deviation_of_slope | standard_deviation_of_slope | wbtools_oss | done | No | Tier: wbtools_oss ¦ Slope variability over neighborhood
topographic_hachures | topographic_hachures | wbtools_pro | done | No | Tier: wbtools_pro ¦ Decorative slope-based rendering
relief | relief | wbtools_oss | done | No | Tier: wbtools_oss ¦ Directional relief metric
relative_topographic_position | relative_topographic_position | wbtools_oss | done | No | Tier: wbtools_oss ¦ Relative elevation percentile
relative_aspect | relative_aspect | wbtools_oss | done | No | Tier: wbtools_oss ¦ Aspect relative to slope direction
elevation_relative_to_min_max | elevation_relative_to_min_max | wbtools_oss | done | No | Tier: wbtools_oss ¦ Normalized elevation (0-1)
elevation_relative_to_watershed_min_max | elevation_relative_to_watershed_min_max | wbtools_oss | done | No | Tier: wbtools_oss ¦ Watershed-relative elevation
elevation_percentile | elevation_percentile | wbtools_oss | done | No | Tier: wbtools_oss ¦ Percentile rank of elevation
max_elevation_deviation | max_elevation_deviation | wbtools_oss | done | No | Tier: wbtools_oss ¦ Max deviation from mean in neighborhood
difference_from_mean_elevation | difference_from_mean_elevation | wbtools_oss | done | No | Tier: wbtools_oss ¦ Individual point vs. mean
max_difference_from_mean | max_difference_from_mean | wbtools_oss | done | No | Tier: wbtools_oss ¦ Max difference in neighborhood
deviation_from_mean_elevation | deviation_from_mean_elevation | wbtools_oss | done | No | Tier: wbtools_oss ¦ Signed elevation deviation
elev_above_pit | elev_above_pit | wbtools_oss | done | No | Tier: wbtools_oss ¦ Elevation above nearest pit
elev_above_pit_dist | elev_above_pit_dist | wbtools_oss | done | No | Tier: wbtools_oss ¦ Distance to nearest pit
percent_elev_range | percent_elev_range | wbtools_oss | done | No | Tier: wbtools_oss ¦ Elevation as % of local range
max_downslope_elev_change | max_downslope_elev_change | wbtools_oss | done | No | Tier: wbtools_oss ¦ Maximum downslope gradient
max_upslope_elev_change | max_upslope_elev_change | wbtools_oss | done | No | Tier: wbtools_oss ¦ Maximum upslope gradient
min_downslope_elev_change | min_downslope_elev_change | wbtools_oss | done | No | Tier: wbtools_oss ¦ Minimum downslope gradient
downslope_index | downslope_index | wbtools_oss | done | No | Tier: wbtools_oss ¦ Downslope flow magnitude metric
num_downslope_neighbours | num_downslope_neighbours | wbtools_oss | done | No | Tier: wbtools_oss ¦ Count of downslope neighbors
num_upslope_neighbours | num_upslope_neighbours | wbtools_oss | done | No | Tier: wbtools_oss ¦ Count of upslope neighbors
relative_stream_power_index | relative_stream_power_index | wbtools_oss | done | No | Tier: wbtools_oss ¦ Stream power index (normalized)
sediment_transport_index | sediment_transport_index | wbtools_oss | done | No | Tier: wbtools_oss ¦ Sediment transport capacity metric
topographic_position_animation | topographic_position_animation | wbtools_pro | done | No | Tier: wbtools_pro ¦ Animated TPI classification
multiscale_topographic_position_image |  | wbtools_oss | done | Yes | Tier: wbtools_oss ¦ Multi-scale TPI; NEW_ENHANCEMENT
multiscale_elevation_percentile |  | wbtools_oss | done | Yes | Tier: wbtools_oss ¦ Multi-scale elevation ranking; NEW_ENHANCEMENT
multiscale_elevated_index |  | wbtools_oss | done | Yes | Tier: wbtools_oss ¦ Multi-scale elevated terrain index; NEW_ENHANCEMENT
multiscale_low_lying_index |  | wbtools_oss | done | Yes | Tier: wbtools_oss ¦ Multi-scale depression index; NEW_ENHANCEMENT
multiscale_roughness |  | wbtools_oss | done | Yes | Tier: wbtools_oss ¦ Multi-scale surface roughness; NEW_ENHANCEMENT
multiscale_roughness_signature |  | wbtools_oss | done | Yes | Tier: wbtools_oss ¦ Multi-scale roughness profile; NEW_ENHANCEMENT
multiscale_std_dev_normals |  | wbtools_oss | done | Yes | Tier: wbtools_oss ¦ Multi-scale surface normal variation; NEW_ENHANCEMENT
multiscale_std_dev_normals_signature |  | wbtools_oss | done | Yes | Tier: wbtools_oss ¦ Multi-scale normal variation profile; NEW_ENHANCEMENT
geomorphons | geomorphons | wbtools_oss | done | No | Tier: wbtools_oss ¦ Landform classification system
pennock_landform_classification | pennock_landform_classification | wbtools_oss | done | No | Tier: wbtools_oss ¦ Pennock ecogeomorphic classification (7 types)
dem_void_filling | dem_void_filling | wbtools_pro | done | No | Tier: wbtools_pro ¦ Interpolate missing DEM data
fill_missing_data | fill_missing_data | wbtools_oss | done | No | Tier: wbtools_oss ¦ Alternative missing-data method
feature_preserving_smoothing | feature_preserving_smoothing | wbtools_oss | done | No | Tier: wbtools_oss ¦ Smooth while preserving edges
find_ridges | find_ridges | wbtools_oss | done | No | Tier: wbtools_oss ¦ Ridge feature extraction
map_off_terrain_objects | map_off_terrain_objects | wbtools_oss | done | No | Tier: wbtools_oss ¦ Identify non-terrain features (buildings, trees)
remove_off_terrain_objects | remove_off_terrain_objects | wbtools_oss | done | No | Tier: wbtools_oss ¦ Filter non-terrain features
smooth_vegetation_residual | smooth_vegetation_residual | wbtools_pro | done | No | Tier: wbtools_pro ¦ Vegetation removal smoothing
edge_density | edge_density | wbtools_oss | done | No | Tier: wbtools_oss ¦ Feature boundary density
breakline_mapping | breakline_mapping | wbtools_pro | done | No | Tier: wbtools_pro ¦ Discontinuity detection
embankment_mapping | embankment_mapping | wbtools_oss | done | No | Tier: wbtools_oss ¦ Embankment/terrace detection
principal_curvature_direction | principal_curvature_direction | wbtools_oss | done | No | Tier: wbtools_oss ¦ Principal curvature orientation
convergence_index | convergence_index | wbtools_oss | done | No | Tier: wbtools_oss ¦ Flow convergence metric
circular_variance_of_aspect | circular_variance_of_aspect | wbtools_oss | done | No | Tier: wbtools_oss ¦ Aspect uniformity metric
average_normal_vector_angular_deviation | average_normal_vector_angular_deviation | wbtools_oss | done | No | Tier: wbtools_oss ¦ Normal vector variability
spherical_std_dev_of_normals | spherical_std_dev_of_normals | wbtools_oss | done | No | Tier: wbtools_oss ¦ Spherical standard deviation of surface normals
unsphericity | unsphericity | wbtools_pro | done | No | Tier: wbtools_pro ¦ Surface sphericity index
shape_index | shape_index | wbtools_pro | done | No | Tier: wbtools_pro ¦ Landform shape index (-1 to 1)
max_anisotropy_dev | max_anisotropy_dev | wbtools_oss | done | No | Tier: wbtools_oss ¦ Maximum directional variation
max_anisotropy_dev_signature | max_anisotropy_dev_signature | wbtools_oss | done | No | Tier: wbtools_oss ¦ Anisotropy signature profile
max_branch_length | max_branch_length | wbtools_oss | done | No | Tier: wbtools_oss ¦ Longest branch from cell
hypsometric_analysis | hypsometric_analysis | wbtools_oss | done | No | Tier: wbtools_oss ¦ Elevation distribution analysis
local_hypsometric_analysis | local_hypsometric_analysis | wbtools_pro | done | No | Tier: wbtools_pro ¦ Local hypsometric analysis
hypsometrically_tinted_hillshade | hypsometrically_tinted_hillshade | wbtools_oss | done | No | Tier: wbtools_oss ¦ Elevation-colored hillshade
low_points_on_headwater_divides | low_points_on_headwater_divides | wbtools_pro | done | No | Tier: wbtools_pro ¦ Drainage divide saddle detection
assess_route | assess_route | wbtools_pro | done | No | Tier: wbtools_pro ¦ Route quality/passability analysis
shadow_image | shadow_image | wbtools_pro | done | No | Tier: wbtools_pro ¦ Aspect-based shadow rendering
shadow_animation | shadow_animation | wbtools_pro | done | No | Tier: wbtools_pro ¦ Animated multi-azimuth shadows
skyline_analysis | skyline_analysis | wbtools_pro | done | No | Tier: wbtools_pro ¦ Skyline extraction from DEM
time_in_daylight | time_in_daylight | wbtools_oss | done | No | Tier: wbtools_oss ¦ Sun exposure duration map
directional_relief | directional_relief | wbtools_oss | done | No | Tier: wbtools_oss ¦ Aspect-specific relief
profile | profile | wbtools_oss | done | No | Tier: wbtools_oss ¦ Cross-section profile extraction
rotor | rotor | wbtools_pro | done | No | Tier: wbtools_pro ¦ Rotational curvature metric
contours_from_raster | contours_from_raster | wbtools_oss | done | No | Tier: wbtools_oss ¦ Vector contour lines from DEM
contours_from_points | contours_from_points | wbtools_oss | done | No | Tier: wbtools_oss ¦ Vector contours from point cloud
topo_render | topo_render | wbtools_pro | done | No | Tier: wbtools_pro ¦ Advanced terrain visualization
generating_function | generating_function | wbtools_pro | done | No | Tier: wbtools_pro ¦ Terrain generation function fitting
multidirectional_hillshade | multidirectional_hillshade | wbtools_oss | done | No | Tier: wbtools_oss ¦ Multi-direction composite hillshade
max_elev_dev_signature | max_elev_dev_signature | wbtools_oss | done | No | Tier: wbtools_oss ¦ Elevation deviation signature curve

## GIS
New_Tool_Name | Legacy_Tool_Name | Port_Tier | Port_Status | Is_New_NonLegacy | Notes | Python_Wrapper_Status
average_overlay | average_overlay | wbtools_oss | done | No | Tier: wbtools_oss ¦ Cell-by-cell average across rasters
count_if | count_if | wbtools_oss | done | No | Tier: wbtools_oss ¦ Count cells matching condition
highest_position | highest_position | wbtools_oss | done | No | Tier: wbtools_oss ¦ Index of highest-value raster per cell
lowest_position | lowest_position | wbtools_oss | done | No | Tier: wbtools_oss ¦ Index of lowest-value raster per cell
max_absolute_overlay | max_absolute_overlay | wbtools_oss | done | No | Tier: wbtools_oss ¦ Maximum absolute value per cell
max_overlay | max_overlay | wbtools_oss | done | No | Tier: wbtools_oss ¦ Maximum value per cell
min_absolute_overlay | min_absolute_overlay | wbtools_oss | done | No | Tier: wbtools_oss ¦ Minimum absolute value per cell
min_overlay | min_overlay | wbtools_oss | done | No | Tier: wbtools_oss ¦ Minimum value per cell
multiply_overlay | multiply_overlay | wbtools_oss | done | No | Tier: wbtools_oss ¦ Cell-by-cell multiplication
percent_equal_to | percent_equal_to | wbtools_oss | done | No | Tier: wbtools_oss ¦ Percentage of cells equal to value
percent_greater_than | percent_greater_than | wbtools_oss | done | No | Tier: wbtools_oss ¦ Percentage of cells greater than value
percent_less_than | percent_less_than | wbtools_oss | done | No | Tier: wbtools_oss ¦ Percentage of cells less than value
pick_from_list | pick_from_list | wbtools_oss | done | No | Tier: wbtools_oss ¦ Select raster by index per cell
standard_deviation_overlay | standard_deviation_overlay | wbtools_oss | done | No | Tier: wbtools_oss ¦ Cell-by-cell standard deviation
sum_overlay | sum_overlay | wbtools_oss | done | No | Tier: wbtools_oss ¦ Cell-by-cell sum across rasters
weighted_overlay | weighted_overlay | wbtools_oss | done | No | Tier: wbtools_oss ¦ Weighted sum of rasters
weighted_sum | weighted_sum | wbtools_oss | done | No | Tier: wbtools_oss ¦ Weighted raster combination
aggregate_raster | aggregate_raster | wbtools_oss | done | No | Tier: wbtools_oss ¦ Reduce resolution by block aggregation
buffer_raster | buffer_raster | wbtools_oss | done | No | Tier: wbtools_oss ¦ Binary buffer around non-zero cells
centroid_raster | centroid_raster | wbtools_oss | done | No | Tier: wbtools_oss ¦ Patch centroid identification
clump | clump | wbtools_oss | done | No | Tier: wbtools_oss ¦ Group contiguous equal-valued cells
nibble | nibble | wbtools_pro | done | No | Tier: wbtools_pro ¦ Fills masked background cells using nearest-neighbour allocation | ported
create_plane | create_plane | wbtools_oss | done | No | Tier: wbtools_oss ¦ Create raster from planar equation
find_lowest_or_highest_points | find_lowest_or_highest_points | wbtools_oss | done | No | Tier: wbtools_oss ¦ Extract extrema as vector points
heat_map | heat_map | wbtools_oss | done | No | Tier: wbtools_oss ¦ Kernel density estimation
hexagonal_grid_from_raster_base | hexagonal_grid_from_raster_base | wbtools_oss | done | No | Tier: wbtools_oss ¦ Hexagonal grid on raster extent
hexagonal_grid_from_vector_base | hexagonal_grid_from_vector_base | wbtools_oss | done | No | Tier: wbtools_oss ¦ Hexagonal grid on vector extent
idw_interpolation | idw_interpolation | wbtools_oss | done | No | Tier: wbtools_oss ¦ Inverse-distance-weighted interpolation
layer_footprint_raster | layer_footprint_raster | wbtools_oss | done | No | Tier: wbtools_oss ¦ Raster layer footprint extraction
layer_footprint_vector | layer_footprint_vector | wbtools_oss | done | No | Tier: wbtools_oss ¦ Vector layer footprint extraction
map_features | map_features | wbtools_oss | done | No | Tier: wbtools_oss ¦ Feature-to-raster mapping
rectangular_grid_from_raster_base | rectangular_grid_from_raster_base | wbtools_oss | done | No | Tier: wbtools_oss ¦ Regular grid on raster extent
rectangular_grid_from_vector_base | rectangular_grid_from_vector_base | wbtools_oss | done | No | Tier: wbtools_oss ¦ Regular grid on vector extent
natural_neighbour_interpolation | natural_neighbour_interpolation | wbtools_oss | done | No | Tier: wbtools_oss ¦ Voronoi-based interpolation
nearest_neighbour_interpolation | nearest_neighbour_interpolation | wbtools_oss | done | No | Tier: wbtools_oss ¦ Nearest-neighbor rasterization
modified_shepard_interpolation | modified_shepard_interpolation | wbtools_oss | done | No | Tier: wbtools_oss ¦ Modified Shepard method (multiquadric RBF)
radial_basis_function_interpolation | radial_basis_function_interpolation | wbtools_oss | done | No | Tier: wbtools_oss ¦ RBF interpolation (thin-plate spline, polyharmonic, etc.)
raster_cell_assignment | raster_cell_assignment | wbtools_oss | done | No | Tier: wbtools_oss ¦ Cell-value assignment workflows
tin_interpolation | tin_interpolation | wbtools_oss | done | No | Tier: wbtools_oss ¦ Triangulation-based interpolation
block_maximum | block_maximum | wbtools_oss | done | No | Tier: wbtools_oss ¦ Block-wise maximum values
block_minimum | block_minimum | wbtools_oss | done | No | Tier: wbtools_oss ¦ Block-wise minimum values
sieve | sieve | wbtools_pro | done | No | Tier: wbtools_pro ¦ Removes small raster patches using clump-area masking and nibble | ported
NEW_ENHANCEMENT_TOOL_1 |  | wbtools_oss | done | Yes | Tier: wbtools_oss ¦ NEW - Beyond legacy count (+1 tool)

## Hydrology
New_Tool_Name | Legacy_Tool_Name | Port_Tier | Port_Status | Is_New_NonLegacy | Notes | Python_Wrapper_Status
breach_depressions_least_cost | breach_depressions_least_cost | wbtools_oss | done | No | Tier: wbtools_oss ¦ Optimal least-cost pit breach carving
breach_single_cell_pits | breach_single_cell_pits | wbtools_oss | done | No | Tier: wbtools_oss ¦ Single-cell feature removal
fill_depressions | fill_depressions | wbtools_oss | done | No | Tier: wbtools_oss ¦ Full depression fill to outlet spill elevation
fill_depressions_planchon_and_darboux | fill_depressions_planchon_and_darboux | wbtools_oss | done | No | Tier: wbtools_oss ¦ Planchon-Darboux multi-direction fill algorithm
fill_depressions_wang_and_liu | fill_depressions_wang_and_liu | wbtools_oss | done | No | Tier: wbtools_oss ¦ Wang-Liu priority-flood algorithm
fill_pits | fill_pits | wbtools_oss | done | No | Tier: wbtools_oss ¦ Lightweight single-cell pit filling
d8_pointer | d8_pointer | wbtools_oss | done | No | Tier: wbtools_oss ¦ D8 steepest-descent pointer
d8_flow_accum | d8_flow_accum | wbtools_oss | done | No | Tier: wbtools_oss ¦ D8 single-direction flow accumulation
dinf_pointer | dinf_pointer | wbtools_oss | done | No | Tier: wbtools_oss ¦ D-Infinity multiple-direction pointer
dinf_flow_accum | dinf_flow_accum | wbtools_oss | done | No | Tier: wbtools_oss ¦ D-Infinity multiple-direction accumulation
fd8_pointer | fd8_pointer | wbtools_oss | done | No | Tier: wbtools_oss ¦ Fully-distributed 8-direction pointer
fd8_flow_accum | fd8_flow_accum | wbtools_oss | done | No | Tier: wbtools_oss ¦ FD8 multiple-direction accumulation
rho8_pointer | rho8_pointer | wbtools_oss | done | No | Tier: wbtools_oss ¦ Rho8 stochastic pointer
rho8_flow_accum | rho8_flow_accum | wbtools_oss | done | No | Tier: wbtools_oss ¦ Rho8 stochastic accumulation
mdinf_flow_accum | mdinf_flow_accum | wbtools_oss | done | No | Tier: wbtools_oss ¦ MD-Infinity triangular multiple-direction accumulation
qin_flow_accumulation | qin_flow_accumulation | wbtools_oss | done | No | Tier: wbtools_oss ¦ Qin gradient-dependent MFD accumulation
quinn_flow_accumulation | quinn_flow_accumulation | wbtools_oss | done | No | Tier: wbtools_oss ¦ Quinn accumulation-dependent MFD
minimal_dispersion_flow_algorithm | minimal_dispersion_flow_algorithm | wbtools_oss | done | No | Tier: wbtools_oss ¦ Minimal dispersion combined direction+accumulation
flow_accum_full_workflow | flow_accum_full_workflow | wbtools_oss | done | No | Tier: wbtools_oss ¦ Complete depression-removal + flow accumulation workflow
d8_mass_flux | d8_mass_flux | wbtools_oss | done | No | Tier: wbtools_oss ¦ D8 mass flux from mass-load raster
dinf_mass_flux | dinf_mass_flux | wbtools_oss | done | No | Tier: wbtools_oss ¦ D-Infinity mass flux
find_noflow_cells | find_noflow_cells | wbtools_oss | done | No | Tier: wbtools_oss ¦ Locate cells with no downstream direction
num_inflowing_neighbours | num_inflowing_neighbours | wbtools_oss | done | No | Tier: wbtools_oss ¦ Count upstream neighbors contributing to cell
find_parallel_flow | find_parallel_flow | wbtools_oss | done | No | Tier: wbtools_oss ¦ Identify multi-directional flow cells
edge_contamination | edge_contamination | wbtools_oss | done | No | Tier: wbtools_oss ¦ Detect edge-of-grid flow artifacts
flow_length_diff | flow_length_diff | wbtools_oss | done | No | Tier: wbtools_oss ¦ Compare flow-path lengths
downslope_flowpath_length | downslope_flowpath_length | wbtools_oss | done | No | Tier: wbtools_oss ¦ Total downstream path length to outlet
max_upslope_flowpath_length | max_upslope_flowpath_length | wbtools_oss | done | No | Tier: wbtools_oss ¦ Longest upstream tributary path
average_upslope_flowpath_length | average_upslope_flowpath_length | wbtools_oss | done | No | Tier: wbtools_oss ¦ Mean upstream path length
elevation_above_stream | elevation_above_stream | wbtools_oss | done | No | Tier: wbtools_oss ¦ Elevation distance to nearest stream
elevation_above_stream_euclidean | elevation_above_stream_euclidean | wbtools_oss | done | No | Tier: wbtools_oss ¦ Euclidean distance to nearest stream
downslope_distance_to_stream | downslope_distance_to_stream | wbtools_oss | done | No | Tier: wbtools_oss ¦ Flow-path distance to stream
average_flowpath_slope | average_flowpath_slope | wbtools_oss | done | No | Tier: wbtools_oss ¦ Mean slope along flow path
max_upslope_value | max_upslope_value | wbtools_oss | done | No | Tier: wbtools_oss ¦ Maximum value in upslope area
longest_flowpath | longest_flowpath | wbtools_oss | done | No | Tier: wbtools_oss ¦ Longest path from highest point to outlet
depth_to_water | depth_to_water | wbtools_oss | done | No | Tier: wbtools_oss ¦ Vertical distance to water surface
fill_burn | fill_burn | wbtools_oss | done | No | Tier: wbtools_oss ¦ Stream burning and DEM conditioning
burn_streams_at_roads | burn_streams_at_roads | wbtools_oss | done | No | Tier: wbtools_oss ¦ Road-stream interaction mapping
trace_downslope_flowpaths | trace_downslope_flowpaths | wbtools_oss | done | No | Tier: wbtools_oss ¦ Flow-path tracing from points
flood_order | flood_order | wbtools_oss | done | No | Tier: wbtools_oss ¦ Flood sequence ordering
insert_dams | insert_dams | wbtools_oss | done | No | Tier: wbtools_oss ¦ Dam insertion points for flow control
raise_walls | raise_walls | wbtools_oss | done | No | Tier: wbtools_oss ¦ Wall elevation for containment
topological_breach_burn | topological_breach_burn | wbtools_oss | done | No | Tier: wbtools_oss ¦ Topology-aware stream conditioning
stochastic_depression_analysis | stochastic_depression_analysis | wbtools_oss | done | No | Tier: wbtools_oss ¦ Random depression characterization
unnest_basins | unnest_basins | wbtools_oss | done | No | Tier: wbtools_oss ¦ Basin nesting analysis
upslope_depression_storage | upslope_depression_storage | wbtools_oss | done | No | Tier: wbtools_oss ¦ Depression water-holding capacity
flatten_lakes | flatten_lakes | wbtools_oss | done | No | Tier: wbtools_oss ¦ Flatten enclosed water bodies
hydrologic_connectivity | hydrologic_connectivity | wbtools_oss | done | No | Tier: wbtools_oss ¦ Hydrologic flow connectivity
impoundment_size_index | impoundment_size_index | wbtools_oss | done | No | Tier: wbtools_oss ¦ Water impoundment area index
depth_in_sink | depth_in_sink | wbtools_oss | done | No | Tier: wbtools_oss ¦ Depth in enclosed depressions
sink | sink | wbtools_oss | done | No | Tier: wbtools_oss ¦ Sink/depression identification
basins | basins | wbtools_oss | done | No | Tier: wbtools_oss ¦ Complete drainage basins from D8 pointer
watershed_from_raster_pour_points | watershed_from_raster_pour_points | wbtools_oss | done | No | Tier: wbtools_oss ¦ Watershed delineation from pour points
watershed | watershed | wbtools_oss | done | No | Tier: wbtools_oss ¦ Watershed delineation (flow-based)
jenson_snap_pour_points | jenson_snap_pour_points | wbtools_oss | done | No | Tier: wbtools_oss ¦ Jenson snap-to-stream algorithm
snap_pour_points | snap_pour_points | wbtools_oss | done | No | Tier: wbtools_oss ¦ Snap outlet points to streams
subbasins | subbasins | wbtools_oss | done | No | Tier: wbtools_oss ¦ Sub-basin delineation
hillslopes | hillslopes | wbtools_oss | done | No | Tier: wbtools_oss ¦ Hillslope feature extraction
strahler_order_basins | strahler_order_basins | wbtools_oss | done | No | Tier: wbtools_oss ¦ Strahler stream-order based basins
isobasins | isobasins | wbtools_oss | done | No | Tier: wbtools_oss ¦ Isocline-based basin isolation

## Remote Sensing
New_Tool_Name | Legacy_Tool_Name | Port_Tier | Port_Status | Is_New_NonLegacy | Notes | Python_Wrapper_Status
adaptive_filter | adaptive_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Adaptive edge-preserving filter
anisotropic_diffusion_filter | anisotropic_diffusion_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Anisotropic diffusion smoothing
balance_contrast_enhancement | balance_contrast_enhancement | wbtools_oss | done | No | Tier: wbtools_oss ¦ Histogram balancing
bilateral_filter | bilateral_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Bilateral smoothing
canny_edge_detection | canny_edge_detection | wbtools_oss | done | No | Tier: wbtools_oss ¦ Canny edge detector
conservative_smoothing_filter | conservative_smoothing_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Conservative smoothing
change_vector_analysis | change_vector_analysis | wbtools_oss | done | No | Tier: wbtools_oss ¦ Multi-temporal change detection
closing | closing | wbtools_oss | done | No | Tier: wbtools_oss ¦ Morphological closing
corner_detection | corner_detection | wbtools_oss | done | No | Tier: wbtools_oss ¦ Corner feature detection
correct_vignetting | correct_vignetting | wbtools_oss | done | No | Tier: wbtools_oss ¦ Vignetting correction
create_colour_composite | create_colour_composite | wbtools_oss | done | No | Tier: wbtools_oss ¦ RGB composite creation
diff_of_gaussians_filter | diff_of_gaussians_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Difference-of-Gaussians filter
direct_decorrelation_stretch | direct_decorrelation_stretch | wbtools_oss | done | No | Tier: wbtools_oss ¦ Decorrelation stretch
diversity_filter | diversity_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Diversity metric filter
edge_preserving_mean_filter | edge_preserving_mean_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Edge-preserving mean filter
emboss_filter | emboss_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Emboss effect
evaluate_training_sites | evaluate_training_sites | wbtools_oss | done | No | Tier: wbtools_oss ¦ Training site validation
fast_almost_gaussian_filter | fast_almost_gaussian_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Approximate Gaussian filter (fast)
flip_image | flip_image | wbtools_oss | done | No | Tier: wbtools_oss ¦ Image flip/rotation
frost_filter | frost_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Frost speckle filter (SAR)
frangi_filter | frangi_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Frangi vessel-like structure filter
fuzzy_knn_classification | fuzzy_knn_classification | wbtools_oss | done | No | Tier: wbtools_oss ¦ Fuzzy k-nearest neighbor
gabor_filter_bank | gabor_filter_bank | wbtools_oss | done | No | Tier: wbtools_oss ¦ Gabor filter bank
generalize_classified_raster | generalize_classified_raster | wbtools_oss | done | No | Tier: wbtools_oss ¦ Raster class generalization
generalize_with_similarity | generalize_with_similarity | wbtools_oss | done | No | Tier: wbtools_oss ¦ Similarity-based generalization
gaussian_contrast_stretch | gaussian_contrast_stretch | wbtools_oss | done | No | Tier: wbtools_oss ¦ Gaussian contrast stretch
gaussian_filter | gaussian_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Gaussian smoothing
gamma_correction | gamma_correction | wbtools_oss | done | No | Tier: wbtools_oss ¦ Gamma radiometric correction
gamma_map_filter | gamma_map_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Gamma mapping filter
guided_filter | guided_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Guided filter
high_pass_filter | high_pass_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ High-pass filter
high_pass_bilateral_filter | high_pass_bilateral_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ High-pass bilateral filter
high_pass_median_filter | high_pass_median_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ High-pass median filter
histogram_equalization | histogram_equalization | wbtools_oss | done | No | Tier: wbtools_oss ¦ Histogram equalization
histogram_matching | histogram_matching | wbtools_oss | done | No | Tier: wbtools_oss ¦ Histogram matching (single image)
histogram_matching_two_images | histogram_matching_two_images | wbtools_oss | done | No | Tier: wbtools_oss ¦ Histogram matching (two images)
ihs_to_rgb | ihs_to_rgb | wbtools_oss | done | No | Tier: wbtools_oss ¦ IHS to RGB color conversion
k_means_clustering | k_means_clustering | wbtools_oss | done | No | Tier: wbtools_oss ¦ K-means unsupervised clustering
k_nearest_mean_filter | k_nearest_mean_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ k-nearest mean filter
knn_classification | knn_classification | wbtools_oss | done | No | Tier: wbtools_oss ¦ k-nearest neighbor classification
knn_regression | knn_regression | wbtools_oss | done | No | Tier: wbtools_oss ¦ k-nearest neighbor regression
logistic_regression | logistic_regression | wbtools_oss | done | No | Tier: wbtools_oss ¦ Logistic regression classification
kuan_filter | kuan_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Kuan speckle filter (SAR)
kuwahara_filter | kuwahara_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Kuwahara edge-preserving filter
image_slider | image_slider | wbtools_oss | done | No | Tier: wbtools_oss ¦ Multi-band image slider
image_segmentation | image_segmentation | wbtools_oss | done | No | Tier: wbtools_oss ¦ Image segmentation/clustering
integral_image_transform | integral_image_transform | wbtools_oss | done | No | Tier: wbtools_oss ¦ Integral image computation
image_stack_profile | image_stack_profile | wbtools_oss | done | No | Tier: wbtools_oss ¦ Multi-band profile/transect
laplacian_filter | laplacian_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Laplacian edge detection
laplacian_of_gaussians_filter | laplacian_of_gaussians_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Laplacian-of-Gaussians filter
lee_filter | lee_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Lee speckle filter (SAR)
line_detection_filter | line_detection_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Line detection filter
line_thinning | line_thinning | wbtools_oss | done | No | Tier: wbtools_oss ¦ Line feature thinning
majority_filter | majority_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Majority/mode filter
maximum_filter | maximum_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Maximum filter (dilation)
mean_filter | mean_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Mean smoothing filter
median_filter | median_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Median filter
min_max_contrast_stretch | min_max_contrast_stretch | wbtools_oss | done | No | Tier: wbtools_oss ¦ Min-max contrast stretch
min_dist_classification | min_dist_classification | wbtools_oss | done | No | Tier: wbtools_oss ¦ Minimum distance classification
minimum_filter | minimum_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Minimum filter (erosion)
modified_k_means_clustering | modified_k_means_clustering | wbtools_oss | done | No | Tier: wbtools_oss ¦ Modified k-means iterative refinement
mosaic | mosaic | wbtools_oss | done | No | Tier: wbtools_oss ¦ Tile mosaic assembly
mosaic_with_feathering | mosaic_with_feathering | wbtools_oss | done | No | Tier: wbtools_oss ¦ Mosaic with feathering
non_local_means_filter | non_local_means_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Non-local means denoising
nnd_classification | nnd_classification | wbtools_oss | done | No | Tier: wbtools_oss ¦ Nearest-neighbor density classification
normalized_difference_index | normalized_difference_index | wbtools_oss | done | No | Tier: wbtools_oss ¦ Vegetation/spectral index calculation
opening | opening | wbtools_oss | done | No | Tier: wbtools_oss ¦ Morphological opening
olympic_filter | olympic_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Olympic filter (exclusion statistics)
otsu_thresholding | otsu_thresholding | wbtools_oss | done | No | Tier: wbtools_oss ¦ Otsu automatic thresholding
panchromatic_sharpening | panchromatic_sharpening | wbtools_oss | done | No | Tier: wbtools_oss ¦ Pan-sharpening fusion
parallelepiped_classification | parallelepiped_classification | wbtools_oss | done | No | Tier: wbtools_oss ¦ Parallelepiped classification
percentage_contrast_stretch | percentage_contrast_stretch | wbtools_oss | done | No | Tier: wbtools_oss ¦ Percentage contrast stretch
piecewise_contrast_stretch | piecewise_contrast_stretch | wbtools_oss | done | No | Tier: wbtools_oss ¦ Piecewise contrast stretch
percentile_filter | percentile_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Percentile filter
prewitt_filter | prewitt_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Prewitt edge detection
random_forest_classification | random_forest_classification | wbtools_oss | done | No | Tier: wbtools_oss ¦ Random forest classification
random_forest_classification_fit | random_forest_classification_fit | wbtools_oss | done | No | Tier: wbtools_oss ¦ Random forest model fitting
random_forest_classification_predict | random_forest_classification_predict | wbtools_oss | done | No | Tier: wbtools_oss ¦ Random forest prediction
random_forest_regression | random_forest_regression | wbtools_oss | done | No | Tier: wbtools_oss ¦ Random forest regression
random_forest_regression_fit | random_forest_regression_fit | wbtools_oss | done | No | Tier: wbtools_oss ¦ Random forest regression fitting
random_forest_regression_predict | random_forest_regression_predict | wbtools_oss | done | No | Tier: wbtools_oss ¦ Random forest regression prediction
range_filter | range_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Range (max-min) filter
rgb_to_ihs | rgb_to_ihs | wbtools_oss | done | No | Tier: wbtools_oss ¦ RGB to IHS color conversion
remove_spurs | remove_spurs | wbtools_oss | done | No | Tier: wbtools_oss ¦ Spur removal from lines
roberts_cross_filter | roberts_cross_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Roberts cross edge detection
resample | resample | wbtools_oss | done | No | Tier: wbtools_oss ¦ Image resampling
savitzky_golay_2d_filter | savitzky_golay_2d_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Savitzky-Golay 2D filter
scharr_filter | scharr_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Scharr edge detection
sigmoidal_contrast_stretch | sigmoidal_contrast_stretch | wbtools_oss | done | No | Tier: wbtools_oss ¦ Sigmoidal contrast stretch
sobel_filter | sobel_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Sobel edge detection
split_colour_composite | split_colour_composite | wbtools_oss | done | No | Tier: wbtools_oss ¦ RGB color decomposition
standard_deviation_contrast_stretch | standard_deviation_contrast_stretch | wbtools_oss | done | No | Tier: wbtools_oss ¦ Std-dev contrast stretch
standard_deviation_filter | standard_deviation_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Standard deviation filter
svm_classification | svm_classification | wbtools_oss | done | No | Tier: wbtools_oss ¦ Support vector machine classification
svm_regression | svm_regression | wbtools_oss | done | No | Tier: wbtools_oss ¦ Support vector machine regression
thicken_raster_line | thicken_raster_line | wbtools_oss | done | No | Tier: wbtools_oss ¦ Raster line thickening
total_filter | total_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Total filter (combined gradient)
tophat_transform | tophat_transform | wbtools_oss | done | No | Tier: wbtools_oss ¦ Top-hat morphological transform
unsharp_masking | unsharp_masking | wbtools_oss | done | No | Tier: wbtools_oss ¦ Unsharp masking sharpening
user_defined_weights_filter | user_defined_weights_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Custom convolution filter
wiener_filter | wiener_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Wiener filter
write_function_memory_insertion | write_function_memory_insertion | wbtools_oss | done | No | Tier: wbtools_oss ¦ (Specialized analysis tool)

## LiDAR Processing
New_Tool_Name | Legacy_Tool_Name | Port_Tier | Port_Status | Is_New_NonLegacy | Notes | Python_Wrapper_Status
lidar_nearest_neighbour_gridding | lidar_nearest_neighbour_gridding | wbtools_oss | done | No | Tier: wbtools_oss ¦ Nearest-neighbor point sampling
lidar_idw_interpolation | lidar_idw_interpolation | wbtools_oss | done | No | Tier: wbtools_oss ¦ Inverse-distance-weighted interpolation
lidar_tin_gridding | lidar_tin_gridding | wbtools_oss | done | No | Tier: wbtools_oss ¦ Delaunay TIN with barycentric interpolation
lidar_radial_basis_function_interpolation | lidar_radial_basis_function_interpolation | wbtools_oss | done | No | Tier: wbtools_oss ¦ RBF (thin-plate spline, polyharmonic, etc.)
lidar_sibson_interpolation | lidar_sibson_interpolation | wbtools_oss | done | No | Tier: wbtools_oss ¦ Sibson/Voronoi natural-neighbor interpolation
lidar_block_maximum | lidar_block_maximum | wbtools_oss | done | No | Tier: wbtools_oss ¦ Block-wise maximum elevation
lidar_block_minimum | lidar_block_minimum | wbtools_oss | done | No | Tier: wbtools_oss ¦ Block-wise minimum elevation
lidar_point_density | lidar_point_density | wbtools_oss | done | No | Tier: wbtools_oss ¦ Point density gridding
lidar_digital_surface_model | lidar_digital_surface_model | wbtools_oss | done | No | Tier: wbtools_oss ¦ DSM from point cloud
lidar_hillshade | lidar_hillshade | wbtools_oss | done | No | Tier: wbtools_oss ¦ Shaded relief from LiDAR
filter_lidar_classes | filter_lidar_classes | wbtools_oss | done | No | Tier: wbtools_oss ¦ Exclude/include LAS classification codes
filter_lidar_noise | filter_lidar_noise | wbtools_oss | done | No | Tier: wbtools_oss ¦ Isolated noise point removal
filter_lidar_scan_angles | filter_lidar_scan_angles | wbtools_oss | done | No | Tier: wbtools_oss ¦ Filter by scan angle range
filter_lidar_by_percentile | filter_lidar_by_percentile | wbtools_oss | done | No | Tier: wbtools_oss ¦ Percentile-based elevation filtering
filter_lidar_by_reference_surface | filter_lidar_by_reference_surface | wbtools_oss | done | No | Tier: wbtools_oss ¦ Filter relative to reference (DTM/DSM)
filter_lidar | filter_lidar | wbtools_oss | done | No | Tier: wbtools_oss ¦ Conditional expression filtering
lidar_thin | lidar_thin | wbtools_oss | done | No | Tier: wbtools_oss ¦ Point thinning (first/last/random returns)
lidar_thin_high_density | lidar_thin_high_density | wbtools_oss | done | No | Tier: wbtools_oss ¦ Density-based thinning
lidar_elevation_slice | lidar_elevation_slice | wbtools_oss | done | No | Tier: wbtools_oss ¦ Elevation range extraction
lidar_remove_outliers | lidar_remove_outliers | wbtools_oss | done | No | Tier: wbtools_oss ¦ Outlier identification and removal
remove_duplicates | remove_duplicates | wbtools_oss | done | No | Tier: wbtools_oss ¦ Duplicate point removal
lidar_join | lidar_join | wbtools_oss | done | No | Tier: wbtools_oss ¦ Merge multiple point clouds
lidar_tile | lidar_tile | wbtools_oss | done | No | Tier: wbtools_oss ¦ Tile point cloud by spatial grid
sort_lidar | sort_lidar | wbtools_oss | done | No | Tier: wbtools_oss ¦ Sort points by attribute
split_lidar | split_lidar | wbtools_oss | done | No | Tier: wbtools_oss ¦ Split cloud by attribute/threshold
lidar_shift | lidar_shift | wbtools_oss | done | No | Tier: wbtools_oss ¦ XYZ coordinate shifting
modify_lidar | modify_lidar | wbtools_oss | done | No | Tier: wbtools_oss ¦ Expression-based point modification
normalize_lidar | normalize_lidar | wbtools_oss | done | No | Tier: wbtools_oss ¦ Height normalization by DTM
height_above_ground | height_above_ground | wbtools_oss | done | No | Tier: wbtools_oss ¦ Height as Z values above ground
lidar_ground_point_filter | lidar_ground_point_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Automated ground classification
classify_lidar | classify_lidar | wbtools_oss | done | No | Tier: wbtools_oss ¦ Multi-stage RANSAC classification (roofs, facades, ground)
classify_overlap_points | classify_overlap_points | wbtools_oss | done | No | Tier: wbtools_oss ¦ Overlapping return classification
classify_buildings_in_lidar | classify_buildings_in_lidar | wbtools_oss | done | No | Tier: wbtools_oss ¦ Building mask enforcement
lidar_classify_subset | lidar_classify_subset | wbtools_oss | done | No | Tier: wbtools_oss ¦ Classify subset matching criteria
lidar_segmentation | lidar_segmentation | wbtools_oss | done | No | Tier: wbtools_oss ¦ Point cloud segmentation
lidar_segmentation_based_filter | lidar_segmentation_based_filter | wbtools_oss | done | No | Tier: wbtools_oss ¦ Segment-aware filtering
clip_lidar_to_polygon | clip_lidar_to_polygon | wbtools_oss | done | No | Tier: wbtools_oss ¦ Polygon-based clipping
erase_polygon_from_lidar | erase_polygon_from_lidar | wbtools_oss | done | No | Tier: wbtools_oss ¦ Polygon-based erasing
select_tiles_by_polygon | select_tiles_by_polygon | wbtools_oss | done | No | Tier: wbtools_oss ¦ Batch polygon selection
lidar_colourize | lidar_colourize | wbtools_oss | done | No | Tier: wbtools_oss ¦ RGB colorization
colourize_based_on_class | colourize_based_on_class | wbtools_oss | done | No | Tier: wbtools_oss ¦ Classification-based coloring
colourize_based_on_point_returns | colourize_based_on_point_returns | wbtools_oss | done | No | Tier: wbtools_oss ¦ Return-count coloring
ascii_to_las | ascii_to_las | wbtools_oss | done | No | Tier: wbtools_oss ¦ ASCII to LAS conversion
las_to_ascii | las_to_ascii | wbtools_oss | done | No | Tier: wbtools_oss ¦ LAS to ASCII conversion
lidar_contour | lidar_contour | wbtools_pro | done | No | Tier: wbtools_pro ¦ Raster-based contour vectorization
lidar_construct_vector_tin | lidar_construct_vector_tin | wbtools_pro | done | No | Tier: wbtools_pro ¦ TIN-based vector output
lidar_hex_bin | lidar_hex_bin | wbtools_pro | done | No | Tier: wbtools_pro ¦ Hexagonal binning with geometry output
lidar_tile_footprint | lidar_tile_footprint | wbtools_pro | done | No | Tier: wbtools_pro ¦ Tile boundary footprints
las_to_shapefile | las_to_shapefile | wbtools_pro | done | No | Tier: wbtools_pro ¦ Point-to-shapefile conversion
lidar_info | lidar_info | wbtools_pro | done | No | Tier: wbtools_pro ¦ LiDAR metadata and statistics reporting
lidar_histogram | lidar_histogram | wbtools_pro | done | No | Tier: wbtools_pro ¦ Attribute distribution histogram
lidar_point_stats | lidar_point_stats | wbtools_pro | done | No | Tier: wbtools_pro ¦ Per-tile point statistics grid
lidar_point_return_analysis | lidar_point_return_analysis | wbtools_pro | done | No | Tier: wbtools_pro ¦ Return-count analysis and reporting
flightline_overlap | flightline_overlap | wbtools_pro | done | No | Tier: wbtools_pro ¦ Flightline overlap detection
recover_flightline_info | recover_flightline_info | wbtools_pro | done | No | Tier: wbtools_pro ¦ Flightline metadata recovery
find_flightline_edge_points | find_flightline_edge_points | wbtools_pro | done | No | Tier: wbtools_pro ¦ Flightline boundary point identification
lidar_tophat_transform | lidar_tophat_transform | wbtools_pro | done | No | Tier: wbtools_pro ¦ Top-hat morphological transform
normal_vectors | normal_vectors | wbtools_pro | done | No | Tier: wbtools_pro ¦ Surface normal vector extraction
lidar_eigenvalue_features | lidar_eigenvalue_features | wbtools_pro | done | No | Tier: wbtools_pro ¦ Eigenvector-based feature metrics
lidar_ransac_planes | lidar_ransac_planes | wbtools_pro | done | No | Tier: wbtools_pro ¦ RANSAC planar surface detection
lidar_rooftop_analysis | lidar_rooftop_analysis | wbtools_pro | done | No | Tier: wbtools_pro ¦ Building roof structure analysis
individual_tree_detection | individual_tree_detection | wbtools_pro | done | No | Tier: wbtools_pro ¦ Tree crown/stem detection
lidar_kappa | lidar_kappa | wbtools_pro | done | No | Tier: wbtools_pro ¦ Classification accuracy assessment
improved_ground_point_filter | improved_ground_point_filter | wbtools_pro | done | No | Tier: wbtools_pro ¦ Multi-stage percentile, TIN, and reference-surface ground filtering | ported
lidar_dem_full_workflow | lidar_dem_full_workflow | (Dormant) | NOT_PORTED | No | Tier: (Dormant) ¦ Legacy dormant exception; not ported ¦ Legacy exception; intentionally not ported.

## Stream Network Analysis
New_Tool_Name | Legacy_Tool_Name | Port_Tier | Port_Status | Is_New_NonLegacy | Notes | Python_Wrapper_Status
strahler_stream_order | strahler_stream_order | wbtools_oss | done | No | Tier: wbtools_oss ¦ Strahler hierarchy (2-order rule)
horton_stream_order | horton_stream_order | wbtools_oss | done | No | Tier: wbtools_oss ¦ Horton order (main-stem emphasis)
hack_stream_order | hack_stream_order | wbtools_oss | done | No | Tier: wbtools_oss ¦ Hack order (outlet-to-headwater counting)
topological_stream_order | topological_stream_order | wbtools_oss | done | No | Tier: wbtools_oss ¦ Topological distance from outlet
shreve_stream_magnitude | shreve_stream_magnitude | wbtools_oss | done | No | Tier: wbtools_oss ¦ Shreve magnitude (headwater summing)
stream_link_identifier | stream_link_identifier | wbtools_oss | done | No | Tier: wbtools_oss ¦ Unique link segment IDs
stream_link_class | stream_link_class | wbtools_oss | done | No | Tier: wbtools_oss ¦ Link type classification (exterior, interior, sink, etc.)
stream_link_length | stream_link_length | wbtools_oss | done | No | Tier: wbtools_oss ¦ Per-link total length
stream_link_slope | stream_link_slope | wbtools_oss | done | No | Tier: wbtools_oss ¦ Per-link average slope
stream_slope_continuous | stream_slope_continuous | wbtools_oss | done | No | Tier: wbtools_oss ¦ Per-cell slope along stream
distance_to_outlet | distance_to_outlet | wbtools_oss | done | No | Tier: wbtools_oss ¦ Flow-path distance to outlet
length_of_upstream_channels | length_of_upstream_channels | wbtools_oss | done | No | Tier: wbtools_oss ¦ Total upstream channel length
tributary_identifier | tributary_identifier | wbtools_oss | done | No | Tier: wbtools_oss ¦ Tributary numbering/labeling
extract_streams | extract_streams | wbtools_oss | done | No | Tier: wbtools_oss ¦ Stream extraction from flow accumulation
extract_valleys | extract_valleys | wbtools_oss | done | No | Tier: wbtools_oss ¦ Valley extraction (lq, jandr, pandd variants)
raster_streams_to_vector | raster_streams_to_vector | wbtools_oss | done | No | Tier: wbtools_oss ¦ Raster to vector stream conversion
rasterize_streams | rasterize_streams | wbtools_oss | done | No | Tier: wbtools_oss ¦ Vector to raster stream rasterization
find_main_stem | find_main_stem | wbtools_oss | done | No | Tier: wbtools_oss ¦ Outlet-to-source main channel tracing
farthest_channel_head | farthest_channel_head | wbtools_oss | done | No | Tier: wbtools_oss ¦ Most-distant headwater identification
long_profile | long_profile | wbtools_oss | done | No | Tier: wbtools_oss ¦ Stream profile from D8 pointer + DEM
long_profile_from_points | long_profile_from_points | wbtools_oss | done | No | Tier: wbtools_oss ¦ Vector point-based profile generation
remove_short_streams | remove_short_streams | wbtools_oss | done | No | Tier: wbtools_oss ¦ Remove stream segments below minimum length
repair_stream_vector_topology | repair_stream_vector_topology | wbtools_pro | done | No | Tier: wbtools_pro ¦ Intersection splitting + dangling arc correction
vector_stream_network_analysis | vector_stream_network_analysis | wbtools_pro | done | No | Tier: wbtools_pro ¦ Network traversal with key-point routing and ridge-cutting
prune_vector_streams | prune_vector_streams | wbtools_pro | done | No | Tier: wbtools_pro ¦ Legacy priority-flood + squared-distance snapping + TUCL thresholding
river_centerlines | river_centerlines | wbtools_pro | done | No | Tier: wbtools_pro ¦ Raster EDT + thinning + endpoint trace + braid correction
burn_streams | burn_streams | wbtools_oss | done | No | Tier: wbtools_oss ¦ Rasterize-and-burn stream vector into DEM workflow | ported
horton_ratios | horton_ratios | wbtools_oss | done | No | Tier: wbtools_oss ¦ Bifurcation, length, area, and slope Horton ratios from stream network | ported
ridge_and_valley_vectors | ridge_and_valley_vectors | wbtools_pro | done | No | Tier: wbtools_pro ¦ DEM-derived ridge and valley centreline extraction workflow | ported

## Math & Statistics
New_Tool_Name | Legacy_Tool_Name | Port_Tier | Port_Status | Is_New_NonLegacy | Notes | Python_Wrapper_Status
abs | abs | wbtools_oss | done | No | Tier: wbtools_oss ¦ Absolute value
arccos | arccos | wbtools_oss | done | No | Tier: wbtools_oss ¦ Inverse cosine (radians)
arcosh | arcosh | wbtools_oss | done | No | Tier: wbtools_oss ¦ Inverse hyperbolic cosine
arcsin | arcsin | wbtools_oss | done | No | Tier: wbtools_oss ¦ Inverse sine (radians)
arctan | arctan | wbtools_oss | done | No | Tier: wbtools_oss ¦ Inverse tangent (radians)
arsinh | arsinh | wbtools_oss | done | No | Tier: wbtools_oss ¦ Inverse hyperbolic sine
artanh | artanh | wbtools_oss | done | No | Tier: wbtools_oss ¦ Inverse hyperbolic tangent
bool_not | bool_not | wbtools_oss | done | No | Tier: wbtools_oss ¦ Logical NOT
ceil | ceil | wbtools_oss | done | No | Tier: wbtools_oss ¦ Round up to integer
cos | cos | wbtools_oss | done | No | Tier: wbtools_oss ¦ Cosine (radians)
cosh | cosh | wbtools_oss | done | No | Tier: wbtools_oss ¦ Hyperbolic cosine
decrement | decrement | wbtools_oss | done | No | Tier: wbtools_oss ¦ Subtract 1 from each cell
exp | exp | wbtools_oss | done | No | Tier: wbtools_oss ¦ Exponential (e^x)
exp2 | exp2 | wbtools_oss | done | No | Tier: wbtools_oss ¦ 2^x exponential
floor | floor | wbtools_oss | done | No | Tier: wbtools_oss ¦ Round down to integer
increment | increment | wbtools_oss | done | No | Tier: wbtools_oss ¦ Add 1 to each cell
is_nodata | is_nodata | wbtools_oss | done | No | Tier: wbtools_oss ¦ Identify nodata cells
ln | ln | wbtools_oss | done | No | Tier: wbtools_oss ¦ Natural logarithm
log10 | log10 | wbtools_oss | done | No | Tier: wbtools_oss ¦ Base-10 logarithm
log2 | log2 | wbtools_oss | done | No | Tier: wbtools_oss ¦ Base-2 logarithm
negate | negate | wbtools_oss | done | No | Tier: wbtools_oss ¦ Negate values (-x)
reciprocal | reciprocal | wbtools_oss | done | No | Tier: wbtools_oss ¦ 1/x reciprocal
round | round | wbtools_oss | done | No | Tier: wbtools_oss ¦ Round to nearest integer
sin | sin | wbtools_oss | done | No | Tier: wbtools_oss ¦ Sine (radians)
sinh | sinh | wbtools_oss | done | No | Tier: wbtools_oss ¦ Hyperbolic sine
sqrt | sqrt | wbtools_oss | done | No | Tier: wbtools_oss ¦ Square root
square | square | wbtools_oss | done | No | Tier: wbtools_oss ¦ x^2 squaring
tan | tan | wbtools_oss | done | No | Tier: wbtools_oss ¦ Tangent (radians)
tanh | tanh | wbtools_oss | done | No | Tier: wbtools_oss ¦ Hyperbolic tangent
to_degrees | to_degrees | wbtools_oss | done | No | Tier: wbtools_oss ¦ Radians to degrees conversion
to_radians | to_radians | wbtools_oss | done | No | Tier: wbtools_oss ¦ Degrees to radians conversion
truncate | truncate | wbtools_oss | done | No | Tier: wbtools_oss ¦ Truncate to integer (towards zero)
add | add | wbtools_oss | done | No | Tier: wbtools_oss ¦ Addition (two rasters)
subtract | subtract | wbtools_oss | done | No | Tier: wbtools_oss ¦ Subtraction (two rasters)
multiply | multiply | wbtools_oss | done | No | Tier: wbtools_oss ¦ Multiplication (two rasters)
divide | divide | wbtools_oss | done | No | Tier: wbtools_oss ¦ Division (two rasters)
modulo | modulo | wbtools_oss | done | No | Tier: wbtools_oss ¦ Modulo operation (remainder)
integer_division | integer_division | wbtools_oss | done | No | Tier: wbtools_oss ¦ Integer division (floor divide)
power | power | wbtools_oss | done | No | Tier: wbtools_oss ¦ Power operation (x^y)
atan2 | atan2 | wbtools_oss | done | No | Tier: wbtools_oss ¦ Two-argument arctangent
bool_and | bool_and | wbtools_oss | done | No | Tier: wbtools_oss ¦ Logical AND
bool_or | bool_or | wbtools_oss | done | No | Tier: wbtools_oss ¦ Logical OR
bool_xor | bool_xor | wbtools_oss | done | No | Tier: wbtools_oss ¦ Logical XOR
equal_to | equal_to | wbtools_oss | done | No | Tier: wbtools_oss ¦ Equality comparison
not_equal_to | not_equal_to | wbtools_oss | done | No | Tier: wbtools_oss ¦ Inequality comparison
less_than | less_than | wbtools_oss | done | No | Tier: wbtools_oss ¦ Less-than comparison
greater_than | greater_than | wbtools_oss | done | No | Tier: wbtools_oss ¦ Greater-than comparison
conditional_evaluation | conditional_evaluation | wbtools_oss | done | No | Tier: wbtools_oss ¦ If-then-else raster expression
pick_from_list | pick_from_list | wbtools_oss | done | No | Tier: wbtools_oss ¦ Select from multi-raster list by index
raster_calculator | raster_calculator | wbtools_oss | done | No | Tier: wbtools_oss ¦ Multi-raster expression evaluation
raster_summary_stats | raster_summary_stats | wbtools_oss | done | No | Tier: wbtools_oss ¦ Summary statistics (mean, std, range, etc.)
raster_histogram | raster_histogram | wbtools_oss | done | No | Tier: wbtools_oss ¦ Raster value histogram
min | min | wbtools_oss | done | No | Tier: wbtools_oss ¦ Minimum value
max | max | wbtools_oss | done | No | Tier: wbtools_oss ¦ Maximum value
quantiles | quantiles | wbtools_oss | done | No | Tier: wbtools_oss ¦ Percentile/quantile values
list_unique_values | list_unique_values | wbtools_oss | done | No | Tier: wbtools_oss ¦ Unique value list (vector attributes)
list_unique_values_raster | list_unique_values_raster | wbtools_oss | done | No | Tier: wbtools_oss ¦ Unique raster values
cumulative_distribution | cumulative_distribution | wbtools_oss | done | No | Tier: wbtools_oss ¦ Cumulative distribution function
z_scores | z_scores | wbtools_oss | done | No | Tier: wbtools_oss ¦ Standardize to z-scores
rescale_value_range | rescale_value_range | wbtools_oss | done | No | Tier: wbtools_oss ¦ Linear rescaling to target range
root_mean_square_error | root_mean_square_error | wbtools_oss | done | No | Tier: wbtools_oss ¦ RMSE calculation
ks_normality_test | ks_normality_test | wbtools_oss | done | No | Tier: wbtools_oss ¦ Kolmogorov-Smirnov normality test
paired_sample_t_test | paired_sample_t_test | wbtools_oss | done | No | Tier: wbtools_oss ¦ Paired t-test (two sample sets)
two_sample_ks_test | two_sample_ks_test | wbtools_oss | done | No | Tier: wbtools_oss ¦ Two-sample KS test
wilcoxon_signed_rank_test | wilcoxon_signed_rank_test | wbtools_oss | done | No | Tier: wbtools_oss ¦ Wilcoxon signed-rank (paired) test
anova | anova | wbtools_oss | done | No | Tier: wbtools_oss ¦ Analysis of variance across groups
attribute_histogram | attribute_histogram | wbtools_oss | done | No | Tier: wbtools_oss ¦ Vector attribute distribution histogram
attribute_scattergram | attribute_scattergram | wbtools_oss | done | No | Tier: wbtools_oss ¦ Attribute scatter plot (XY relationship)
attribute_correlation | attribute_correlation | wbtools_oss | done | No | Tier: wbtools_oss ¦ Attribute pairwise correlations
cross_tabulation | cross_tabulation | wbtools_oss | done | No | Tier: wbtools_oss ¦ Contingency table analysis
phi_coefficient | phi_coefficient | wbtools_oss | done | No | Tier: wbtools_oss ¦ Phi association coefficient
kappa_index | kappa_index | wbtools_oss | done | No | Tier: wbtools_oss ¦ Cohen's kappa classification agreement
crispness_index | crispness_index | wbtools_oss | done | No | Tier: wbtools_oss ¦ Classification crispness metric
image_correlation | image_correlation | wbtools_oss | done | No | Tier: wbtools_oss ¦ Raster image correlation
image_autocorrelation | image_autocorrelation | wbtools_oss | done | No | Tier: wbtools_oss ¦ Raster spatial autocorrelation
image_correlation_neighbourhood_analysis | image_correlation_neighbourhood_analysis | wbtools_oss | done | No | Tier: wbtools_oss ¦ Neighborhood autocorrelation analysis
image_regression | image_regression | wbtools_oss | done | No | Tier: wbtools_oss ¦ Regression between two rasters
random_forest_classification | random_forest_classification | wbtools_oss | done | No | Tier: wbtools_oss ¦ Random forest classifier
random_forest_classification_fit | random_forest_classification_fit | wbtools_oss | done | No | Tier: wbtools_oss ¦ Random forest model fitting
random_forest_classification_predict | random_forest_classification_predict | wbtools_oss | done | No | Tier: wbtools_oss ¦ Random forest prediction
random_forest_regression | random_forest_regression | wbtools_oss | done | No | Tier: wbtools_oss ¦ Random forest regression
random_forest_regression_fit | random_forest_regression_fit | wbtools_oss | done | No | Tier: wbtools_oss ¦ Random forest model fitting
random_forest_regression_predict | random_forest_regression_predict | wbtools_oss | done | No | Tier: wbtools_oss ¦ Random forest prediction
svm_classification | svm_classification | wbtools_oss | done | No | Tier: wbtools_oss ¦ Support vector machine classification
svm_regression | svm_regression | wbtools_oss | done | No | Tier: wbtools_oss ¦ Support vector machine regression
logistic_regression | logistic_regression | wbtools_oss | done | No | Tier: wbtools_oss ¦ Logistic regression classifier
dbscan | dbscan | wbtools_oss | done | No | Tier: wbtools_oss ¦ DBSCAN clustering algorithm
principal_component_analysis | principal_component_analysis | wbtools_oss | done | No | Tier: wbtools_oss ¦ PCA dimension reduction
inverse_pca | inverse_pca | wbtools_oss | done | No | Tier: wbtools_oss ¦ Inverse PCA reconstruction
trend_surface | trend_surface | wbtools_oss | done | No | Tier: wbtools_oss ¦ Polynomial trend surface fitting
trend_surface_vector_points | trend_surface_vector_points | wbtools_oss | done | No | Tier: wbtools_oss ¦ Trend surface from vector points
turning_bands_simulation | turning_bands_simulation | wbtools_oss | done | No | Tier: wbtools_oss ¦ Stochastic field simulation
zonal_statistics | zonal_statistics | wbtools_oss | done | No | Tier: wbtools_oss ¦ Zone-based summary statistics
inplace_add | inplace_add | wbtools_oss | done | No | Tier: wbtools_oss ¦ In-place raster addition
inplace_subtract | inplace_subtract | wbtools_oss | done | No | Tier: wbtools_oss ¦ In-place raster subtraction
inplace_multiply | inplace_multiply | wbtools_oss | done | No | Tier: wbtools_oss ¦ In-place raster multiplication
inplace_divide | inplace_divide | wbtools_oss | done | No | Tier: wbtools_oss ¦ In-place raster division
random_field | random_field | wbtools_oss | done | No | Tier: wbtools_oss ¦ Random field generation
random_sample | random_sample | wbtools_oss | done | No | Tier: wbtools_oss ¦ Random point sampling
hdbscan_clustering | hdbscan_clustering | (Legacy_Exception) | NOT_PORTED | No | Tier: (Legacy_Exception) ¦ INTENTIONAL EXCEPTION: Failed legacy experiment; excluded from new backend ¦ Legacy exception; intentionally not ported.